## PS&E to NTP
PS&E to Completion Date Contract Time Calculator
Activity Name | Normal Durations (Days) | Minimum Durations (Days) | Contract Durations (Days) | Start Date | Finish Date
PS&E to Advertisement | 25 | 7 | 25 | 2007-01-01 | 2007-01-25
Advertisement to Bid Opening | 30 | 30 | 30 | 2007-01-26 | 2007-02-24
Bid Opening to Notice of Award | 21 | 7 | 21 | 2007-02-25 | 2007-03-17
Contract Award to Execution | 20 | 20 | 20 | 2007-03-18 | 2007-04-06
Execution to Preconstruction Meeting | 62 | 45 | 62 | 2007-04-07 | 2007-06-07
Notice to Proceed to First Chargeable Day | 10 | 1 | 10 | 2007-06-08 | 2007-06-17
Construction Days & Completion Date |  |  | 200 | 2007-06-17 | 2008-01-03
Notes:
1) Enter "Start Date", "Construction Days" and "Contract Durations" values as indicated in yellow.
2) Unless otherwise directed, the "Contract Durations" values should be equal to the values found under the "Normal Durations" column.
Formulas:
Finish Date = ([Start Date]+[Contract Durations (Days)])-1
Finish Date = [Finish Date, row above]+[Contract Durations (Days)]
Start Date = [Finish Date, row above]+1
Start Date = [Finish Date, row above]