## Slide 1: SCR 48, Utilities Working Group Summary
2020 utility summit - February 25, 2020

## Slide 2: Senate Concurrent Resolution (SCR) 48
Created the Utilities Coordination Working Group on 5/16/19 consisting of representation from Senate, DelDOT, DPL, DEC, VZ, Chpk, AWC, Comcast, DEMEC, DCA & ACEC were all outlined
Tasked with recommending measures to shorten the total time to coordinate & implement utility relocations on transportation projects
Required at least a subgroup on design and another on construction
Deadline for recommendations set as 1/1/20
Notes: Some of the previous survey questions:
Would additional reimb expedite relocations?
Would funding design consultants expedite responses and relocations?
Would funding work crews at utility companies expedite relocations?
Could DelDOT perform utility work under highway contracts?
Would an incentive/disincentive approach based on performance be attractive?

## Slide 3: SCR 48 Timeline
First meeting held on 8/21/19
      Working Group Chaired by DelDOT
Broke into 3 subcommittees
      Subcommittee on Design Phase (Chpk Chaired)
      Subcommittee on Construction Phase (DCA Chaired)
      Subcommittee on Technology (DelDOT Chaired)
Working Group mtgs held monthly (5 held)
Subcommittee mtgs held biweekly (13 held)
Last meeting held on 1/8/20
Final Report sent to Working Group on 1/29/20 (5 months)

## Slide 4: Design Subcommittee recommendations
Continuing Working Group in the form of the Delaware Utility Coordination Council
      Perform post design analysis of projects
      Compare & coordinate milestones of the DelDOT design process and the utility design process
      Perform post construction analysis of projects
Determining accountability/incentive measures for design process
Provide DelDOT to provide CAD files with every design milestone submission (utility responses preferred in CAD)

## Slide 5: Design recommendations (Cont.)
Updated plan response timeframes
      Surveys = 30 calendar days (no change)
      Preliminary = 90 calendar days
      Semi-final = 90 calendar days
      Final = 30 calendar days
      If design plans are substantially revised and resubmitted to companies, times reset
Utilities to provide property right documentation within 60 calendar days after receiving survey plans
Plans provided to utility companies to show utilities in accordance with APWA color code

## Slide 6: Design recommendations (Cont.)
Hold constructability/phasing meetings with utility companies between semi-finals & finals
DelDOT to create plan design milestone between preliminary and semi-final plans
      Company response = 90 calendar days
DelDOT to supply composite/overall roll plan of entire project with each plan submission
DelDOT plans will be updated within 30 calendar days of receiving utility company mark-ups/designs
      Utility company will review and confirm updated plans within 14 calendar days

## Slide 7: Design recommendations (Cont.)
DelDOT to utilize dedicated personnel to QA/QC plans
DelDOT to create sustainable funding source to better and more reliably support long term planning so companies can plan and staff accordingly
DelDOT to implement integrated project management technology to better the coordination process

## Slide 8: Construction recommendations
Where companies do not have capabilities, DelDOT to take lead and utilize joint trench when feasible
Once highway contract is awarded, precon to be held between DelDOT, utility companies and highway contractor to discuss schedules, phasing and constructability
      These meeting shall include field walkouts of job
DelDOT to keep & periodically exchange updated project contact lists with utilities, DelDOT and contractor contacts
DelDOT to establish a contractor plan change coordination and approval process

## Slide 9: Construction recommendations (Cont.)
Where feasible, seek to find consensus opportunities to allow highway contractor to perform utility relocation work
DelDOT to create reliable project construction schedules which include utility relocation information
Contractors to provide reliable updates to DelDOT and utility companies throughout project construction
Determine accountability/incentive measures that hold DelDOT, contractors and utility companies accountable

## Slide 10: Construction recommendations (Cont.)
Incorporate construction related discussions early into the design preparation/coordination to determine needs and responsibilities
      Advanced relocation
      Right-of-Way/Easements
      Joint Trenching
      Clearing
      Grubbing
      Cuts/Fills
      Permitting

## Slide 11: Technology recommendations
Existing UPA system needs to be updated to meet needs of utility coordination associated with DelDOT projects
      Enhance UPA to meet needs
      Procure new off-the-shelf system
      Create new, custom developed system
New or updated system will be coordinated with all stakeholders and it is intended to:
      Be reachable from any modern, supported browser or mobile operating system
      Utilize a workflow process from planning through design and construction

## Slide 12: Technology recommendations (Cont.)
      Serve as the end-to-end system of record for aspects of accountability and enforcement
      Allow integration to external systems used by utility companies, to enable data sharing
      Be highly configurable to meet needs of users
      Support scheduling for projects via import and otherwise while also providing access to all project and utility plans
      Track incomplete submissions from DelDOT project designers and utility companies alike, utilizing built-in checklists and other field controls.
      Provide the Utility Conflict Matrix (UCM) as a required system checklist item.

## Slide 13: Technology recommendations (CONT.)
      Support configurable notifications and reminders to aid in accountability
      Provide real-time status of projects via user-configurable dashboard, including reporting capabilities
      Means to search across projects, providers or other key attributes
      Ability to maintain an archive for projects in system
      Provide a map/geospatial component to show project and utility locations with the ability to import existing GIS data from other sources
      Accommodate mapping for all new and relocated utilities

## Slide 14: Technology recommendations (CONT.)
      Enable capture of all assets within the ROW, regardless of whether associated with a highway project
      Provide a means for users to contact each other in reference to projects, with a record of all collaboration housed within
          This shall include functionality to extend and appeal established dates where justified
      Take into consideration the utility companies’ internal processes and restrictions around onboarding and usage of new technology

## Slide 15: DelDOT recommendations
Utility permits work or approvals will be suspended as necessary to maintain compliance with deadlines and schedules related to DelDOT projects in design and construction
DelDOT shall provide resources to companies as necessary to maintain required design schedules
      Reimburse the utility to hire in-house personnel or consultants
      DelDOT to hire utility design consultants to perform relocation designs on behalf of and in consultation with utility companies
      Reimburse the utility for costs incurred performing design work with existing in-house or consulting staff
      These resources will only be provided if required project information is provided within agreed upon timeframes

## Slide 16: DelDOT recommendations (Cont.)
DelDOT may incentivize relocation work or otherwise provide resources or reimbursement to utility companies to ensure agreed upon relocation schedules are maintained or completed earlier than scheduled
DelDOT will pay full costs of any utility relocation work that companies allow to be added directly into the highway project and installed by the highway contractor
Should DelDOT change their proposed design or bid advertisement date, DelDOT will be:
      Responsible for full reimbursement of any costs incurred by the utility company for said project to date of change

## Slide 17: DelDOT recommendations (Cont.)
      Required to give companies adequate time to perform work in accordance with new project schedules
      Required to pay additional fees to utility companies to prioritize relocation needs
Utility companies will be required to use DelDOT’s electronic system to coordinate all highway projects in order to be eligible for incentivized and resource reimbursement
Utility companies will provide DelDOT with detailed and accurate utility relocation schedules that break out work activities/milestones and durations during design coordination
      Will prepare a utility relocation bar chart at the semi-final plan milestone

## Slide 18: DelDOT recommendations (Cont.)
      Relocation bar chart will be incorporated into DelDOT’s overall highway project schedules and timing statement
      Foundation for utility agreements and tracking
      Foundation for highway contractor’s construction schedule
Highway contractor required to coordinate any proposed schedule or phasing changes with utility companies prior to submitting change to DelDOT
      Looking for written agreement from companies
      If DelDOT sees value in proposed changes without consent from companies, DelDOT will coordinate further with companies and may participate with additional costs

## Slide 19: DelDOT recommendations (Cont.)
      Contractor to submit schedules outlining all changes and accurate times/durations as part of this process
Highway contractor required to provide accurate schedules to DelDOT and utility companies for all projects they are involved with
      Include start/end/duration of the contractor’s proposed work activities, construction phases and utility relocation work (whether advanced or concurrent)
      Utility information shall be based on durations, activities, and information provided in the highway contract documents
      Contractor shall submit schedules to DelDOT and companies periodically

## Slide 20: Next Steps
Awaiting insight from Legislature
Will conduct internal and external meeting to work through implementation
More to follow

## Slide 21: Thank you!
Eric Cimo, P.E., DelDOT Utility Engineer
eric.cimo@delaware.gov, 302 760-2642