## Stage 2
Delivery Schedule (Form E)
The evaluation should consider the overall project schedule from scoping through design, construction and opening to the public
DESIGN-BID-BUILD
Complete design and procure the Contractor
Opportunities |  | Obstacles |  | Rating
FALSE | Schedule more predictable and more manageable | FALSE | Longer time linear process
|  | FALSE | Lack industry input could add time
FALSE | Elements of design are completed prior to permitting, construction, etc. | FALSE | Design lead to change orders and schedule delays
FALSE | Shortest contractor procurement period | FALSE | Low bid selection may lead to potential delays and other adverse outcomes
FALSE | Time to communicate/discuss design with stakeholders
FALSE | Milestones can be easier to define
DESIGN-BUILD
D/B procured after 30% plans (NEPA approval)
Opportunities |  | Obstacles |  | Rating
FALSE | Accelerate schedule through parallel process | FALSE | RFP development and procurement can be intensive
FALSE | Shifting schedule risk to DB team | FALSE | Undefined events or conditions found after procurement, but during design can impact schedule and cost
FALSE | Encumbers contruction funds more quickly
FALSE | Industry innovation into design and schedule
|  | FALSE | Requires agency and stakeholder commitment to expedite design review
FALSE | More efficient procurement of long-lead items
|  | FALSE | Design not under direct control of the owner
FALSE | Phased Design allows to start construction earlier
FALSE | Allows innovation in recouce loading and scheduling by DB team
CM/GC
Designer/Contractor begin work together at 50% plans
Opportunities |  | Obstacles |  | Rating
FALSE | Ability to start pieces of construction or procurement of long lead items before entire design, ROW, etc. is complete (i.e. phased design) | FALSE | Potential for not reaching GMP and substantially delaying schedule
|  | FALSE | Designer-contractor-agency disagreements can add delays
FALSE | Early identification and resolution of design and contruction issues (e.g., utility, ROW, and earthwork) | FALSE | Strong agency management is required to control schedule
|  | FALSE | Design Changes/NOIs due to contractor input
FALSE | Shorter procurement then DB
FALSE | Team involvement for schedule optimization
FALSE | Continuous constructability review and VE
FALSE | Contractor input for phasing, constructability and traffic control may reduce overall schedule
Project Complexity/Innovation (Form F)
The evaluation should consider opportunities and timeframes of when issues and innovation can be addressed and resolved.
DESIGN-BID-BUILD
Fully resolve issues during design; innovation through VE and bidding options
Opportunities |  | Obstacles |  | Rating
FALSE | Agencies can have more control of design of complex projects | FALSE | Innovations can add cost or time and restrain contractor's benefits
FALSE | Agency and consultant expertise can select innovation independently of contractor abilities | FALSE | No contractor input to optimize costs
|  | FALSE | Limited flexibility for integrated design and construction solutions (limited to constructability)
FALSE | Opportunities for value engineering studies during design, more time for design solutions
|  | FALSE | Difficult to assess contruction time and cost due to innovation
FALSE | Aids in consistency and maintainability | FALSE | Cannot design to a contractor's strength
FALSE | Full control in selection of design expertise
FALSE | Complex design is resolved and competitively bid
DESIGN-BUILD
Allows Contractor innovation in design development; utilizes ATCs in bidding
Opportunities |  | Obstacles |  | Rating
FALSE | Designer and contractor collaborate to optimize means and methods and enhance innovation | FALSE | Requires desired solutions to complex designs to be well defined through technical requirements (difficult to do)
FALSE | Opportunity for innovation through draft RFP, best value, and ATC processes | FALSE | Qualitative designs are difficult to define (example. aesthetics) Need to be prescribed in RFP
FALSE | Can use best-value procurement to select designbuilder with best qualifications
|  | FALSE | Risk of time or cost constraints on designer inhibiting innovation
FALSE | Constructability and VE inherent in process | FALSE | Some design solutions might be too innovative or unacceptable
FALSE | Early team integration | FALSE | Quality assurance for innovative processes are difficult to define in RFP
FALSE | Sole point of responsibility
CM/GC
Jointly address complex innovative designs through three-party collaboration
Opportunities |  | Obstacles |  | Rating
FALSE | Allows for agency control of a designer/contractor process for developing innovative solutions | FALSE | Designer/CM relationship critical
|  | FALSE | No contractual relationship between designer/CM
FALSE | Allows for an independent selection of the best qualified designer and best qualified contractor | FALSE | Innovations can add cost or time
|  | FALSE | Scope additions difficult to manage
|  | FALSE | Preconstruction services fees for contractor involvement
FALSE | VE inherent in process and enhanced constructability
|  | FALSE | Cost competitiveness – sole source negotiated GMP
FALSE | Risk of innovation can be better defined, minimized, and allocated
FALSE | Can take to market for bidding as contingency
Design Completion (Form G)
The evaluation should consider the level of completed design and its value to the project attributes.
DESIGN-BID-BUILD
100% design by DelDOT
Opportunities |  | Obstacles |  | Rating
FALSE | 100% design by agency | FALSE | Agency design errors can result in a higher number of change orders, claims, etc.
FALSE | Agency has complete control over the design (can be beneficial when there is one specific solution for a project)
|  | FALSE | Minimizes competitive innovation opportunities
FALSE | Project/scope can be developed through design | FALSE | Can reduce level of constructability since the contractor does not buy into the project until after design is complete
FALSE | The scope of the project is well defined through complete plans and contract documents
FALSE | Well-known process to the industry
DESIGN-BUILD
Design advanced to 30% (NEPA) and completed by DB Team
Opportunities |  | Obstacles |  | Rating
FALSE | Design advanced by the agency to level necessary to precisely define the contract requirements and properly allocate risk | FALSE | Must have clear definitions and requirements in the RFP because it is the basis for the contract
|  | FALSE | If design is too far advanced, it will limit the advantages of design-build
FALSE | Does not require much design to be completed before awarding project to the design-builder (between ~ 10% - 30% complete)
|  | FALSE | Potential for lacking or missing scope definition if RFP not carefully developed
|  | FALSE | Overutilizing performance specifications to enhance innovation can risk quality through reduced technical requirements
FALSE | Contractor involvement in early design, which improves constructability and innovation
|  | FALSE | Less agency control over the design
FALSE | Plans do not have to be as detailed because the design-builder is bought into the project early in the process and will accept design responsibility | FALSE | Can create project less standardized designs across agency as a whole
CM/GC
50% design prior to Contractor procurement; remainder completed in collaboration
Opportunities |  | Obstacles |  | Rating
FALSE | Can utilize a lower level of design prior to selecting a contractor then collaboratively advance design with agency, designer and contractor | FALSE | Teaming and communicating concerning design can cause disputes
|  | FALSE | Three party process can slow progression of design
FALSE | Contractor involvement in early design improves constructability | FALSE | If design is too far advanced, it will limit the advantages of CM/GC or could require design backtracking
FALSE | Agency controls design
FALSE | Design can be used for DBB if the price is not successfully negotiated
FALSE | Design can be responsive to risk minimization
Costs (Form H)
The evaluation should review the financial considerations of design, construction, potential change orders, and other project-related costs.
DESIGN-BID-BUILD
Competitive low bid based on designer calcs typical; potential change orders
Opportunities |  | Obstacles |  | Rating
FALSE | Competitive bidding provides a low-cost construction to a fully defined scope of work | FALSE | Cost accuracy is limited until design is completed
|  | FALSE | Cost reductions due to contractor innovation and constructability is difficult to obtain
FALSE | Increase certainty about cost estimates
FALSE | Construction costs are contractually set before construction begins
|  | FALSE | More potential of cost change orders due to Agency design responsibility
DESIGN-BUILD
Fixed budget determined at Contractor selection
Opportunities |  | Obstacles |  | Rating
FALSE | Contractor input into design should moderate cost | FALSE | Risks related to design-build, lump sum cost without 100% design complete, can compromise financial success of the project
FALSE | Design-builder collaboration and ATCs can provide a cost-efficient response to project goals
|  | FALSE | Lack of Stipends may eliminate competition
FALSE | Costs are contractually set early in design process with design-build proposal
FALSE | Allows a variable scope/bid to match a fixed budget
FALSE | Potential lower average cost growth
FALSE | Funding can be obligated in a very short timeframe
FALSE | Stipends can foster better ATC’s
CM/GC
Collaborated price determination; non-competitive negotiated GMP
Opportunities |  | Obstacles |  | Rating
FALSE | Agency/designer/contractor collaboration to reduce project risk can result in lowest project costs | FALSE | Non-competitive negotiated GMP introduces price risk
|  | FALSE | Difficulty in GMP negotiation introduces risk that GMP will not be successfully executed, requiring aborting the CM/GC process
FALSE | Early contractor involvement can result in cost savings through VE and constructability
FALSE | Cost will be known earlier when compared to DBB | FALSE | Paying for contractors’ involvement in the design phase may increase total cost
FALSE | Integrated design/construction process can provide a cost-efficient strategy to project goals | FALSE | Prescribed design elements can lead to cost increases
FALSE | Can provide a cost-efficient response to the project goals
Risk (Form I)
The evaluation should consider the risks including number, complexity, and probability.
DESIGN-BID-BUILD
More control during design; project liability in time and dollars for omissions in construction
Opportunities |  | Obstacles |  | Rating
FALSE | Risks managed separately through design, bid, build is expected to be easier | FALSE | Agency accepts risks associated with project complexity and unknowns
|  | FALSE | Low-bid related risks
FALSE | Risk allocation is most widely understood/used | FALSE | Misplaced risk through prescriptive specs
FALSE | 100% design mitigates some risk | FALSE | Innovative risk allocation difficult to obtain
FALSE | Risk related to environmental, railroad, & third-party involvement best resolved before procurement
|  | FALSE | Limited industry input in risk allocation
|  | FALSE | Change order risks can be greater
FALSE | Utilities/ROW best allocated to the agency and mostly addressed prior to procurement | FALSE | Contractor may avoid risks
DESIGN-BUILD
RFP needs to be detailed in performance requirements; manage risk for best party
Opportunities |  | Obstacles |  | Rating
FALSE | Performance specs allow for alternative risk allocations to the design builder | FALSE | Need a detailed RFP to get comprehensive responses to the RFP (Increased RFP costs may limit bidders)
FALSE | Risk-reward structure better defined
FALSE | Innovative opportunities to allocate risks to most appropriate parties (e.g., schedule, phasing) | FALSE | Limited time to resolve risks
|  | FALSE | Risks allocated to designers for errors and omissions, claims for change orders
FALSE | Opportunity for industry review of risk allocation (draft RFP, ATC processes)
|  | FALSE | Unknowns and associated risks need to be carefully allocated through a welldefined scope and contract
FALSE | Avoid low-bid risk in procurement
FALSE | Contractor helps identify risks with environmental, railroads, ROW, and utilities
|  | FALSE | Poorly defined risks are expensive
|  | FALSE | Contractor may decrease consultant fees at risk to quality
FALSE | Design-Build team can work toward innovative solutions to, or avoidance of, unknowns
CM/GC
Balance risk management through collaborative efforts
Opportunities |  | Obstacles |  | Rating
FALSE | Contractor better understands of the unknown conditions as design progresses | FALSE | Low motivation to manage small quantity $$
|  | FALSE | Increase costs for non-proposal items
FALSE | Innovative opportunities to allocate risks to different parties (e.g., schedule, phasing) | FALSE | If GMP not reached, additional low-bid risks
|  | FALSE | Limited to risk capabilities of CM/GC
FALSE | Chance to manage cost risks through CM/GC input | FALSE | Designer-contractor-agency disagreements can add delays
FALSE | Contractor will help identify and manage risk | FALSE | Strong agency management is required to negotiate/optimize risks
FALSE | Agency still has considerable involvement with third parties to deal with risks | FALSE | Discovery of unknown conditions can drive up GMP, which can be compounded in phased construction
FALSE | Avoids low-bid risk in procurement
FALSE | More flexibility and innovation available to deal with unknowns early in design process

## Stage 3
Staff Experience and Availability (Form J)
The evaluation should consider staff’s experience with various delivery methods and availability to participate in all phases.
DESIGN-BID-BUILD
Various resources spread out over development, design, and construction phases
Opportunities |  | Obstacles |  | Rating
FALSE | Agency, contractors, and consultants have high level of experience with the traditional system | FALSE | Can require a high level of agency staffing of technical resources
|  | FALSE | Staff’s responsibilities are spread out over a longer design period
FALSE | Designers can be more interchangeable between projects
|  | FALSE | Can require staff to have full breadth of technical expertise
DESIGN-BUILD
Critical technical needs during RFQ and RFP stages; design and construction need throughout
Opportunities |  | Obstacles |  | Rating
FALSE | Less agency staff required due to the sole source nature of DB | FALSE | Limitation of availability of staff with skills, knowledge, and personality to manage DB projects
FALSE | Opportunity to grow agency skill levels for staff by learning a new process
|  | FALSE | Existing staff may need additional training to address their changing roles
|  | FALSE | Need to “mass” agency management and technical resources at critical points in process (e.g., RFP development, design reviews)
CM/GC
Strong Agency commitment through collaborative process throughout
Opportunities |  | Obstacles |  | Rating
FALSE | Agency can improve efficiencies by having more project managers on staff rather than specialized experts | FALSE | Strong committed agency project management is important to success
|  | FALSE | Limitation of availability of staff with skills, knowledge, and personality to manage CM/GC projects
FALSE | Smaller number of technical staffs are required through use of consultant designer
|  | FALSE | Existing staff may need additional training to address their changing roles
|  | FALSE | Agency must learn how to negotiate a Proposed Construction Price (PCP)
Oversight and Control Levels (Form K)
The evaluation should consider Agency monitoring and control during design and construction phases.
DESIGN-BID-BUILD
Full control over linear design and construction process
Opportunities |  | Obstacles |  | Rating
FALSE | Full agency control over a linear design and construction process | FALSE | Requires a high-level of oversight
|  | FALSE | Increased likelihood of claims due to agency design responsibility
FALSE | Oversight roles are well understood
FALSE | Contract documents are typically completed in a single package before construction begins | FALSE | Limited control over an integrated design/construction process
FALSE | Multiple checking points through three linear phases: design-bid-build
FALSE | Maximum control over design
DESIGN-BUILD
Performance specs lead to less control in design; QA performed in construction by DB
Opportunities |  | Obstacles |  | Rating
FALSE | A single entity responsibility during project design and construction | FALSE | Can require a high level of design oversight
|  | FALSE | Can require a high level of quality assurance oversight
FALSE | Continuous execution of design and build
|  | FALSE | Limitation on staff with DB oversight experience
FALSE | Getting input from construction to enhance constructability and innovation
|  | FALSE | Less agency control over design
FALSE | Overall project planning and scheduling is established by one entity | FALSE | Control over design relies on proper development of technical requirements
CM/GC
Most control by Agency in design, construction, and collaborative Project Team
Opportunities |  | Obstacles |  | Rating
FALSE | Preconstruction services are provided by the construction manager | FALSE | Agency must have experienced staff to oversee the CM/GC
FALSE | Getting input from construction to enhance constructability and innovation | FALSE | Higher level of cost oversight required
FALSE | Provides agency control over an integrated design/construction process
Competition and Contractor Experience (Form L)
The evaluation should consider available competition levels; availability; and experience of contracting community relative to project type, complexity, and capacity to perform the work.
DESIGN-BID-BUILD
High level of competition and experience; selection typically low-price based
Opportunities |  | Obstacles |  | Rating
FALSE | Promotes a high level of competition in the marketplace | FALSE | Risks associated with selecting the low bid (the best contractor is not necessarily selected)
FALSE | Opens construction to all reasonably qualified bidders
|  | FALSE | No contractor input into the process
FALSE | Transparency and fairness | FALSE | Limited ability to select contractor based on qualifications
FALSE | Reduced chance of corruption and collusion
FALSE | Contractors are familiar with DBB process
DESIGN-BUILD
Balance of price and non-price selection factors; experience varies by project type
Opportunities |  | Obstacles |  | Rating
FALSE | Allows for a balance of qualifications and cost in design-builder procurement | FALSE | Need for DB qualifications can limit competition
FALSE | Two-phase process can promote strong teaming to obtain “Best Value” | FALSE | Lack of competition with experience with the project delivery method
FALSE | Increased opportunity for innovation possibilities due to the diverse project team | FALSE | Reliant on DB team selected for the project
|  | FALSE | The gap between agency experience and contractor experience with delivery method can create conflict
CM/GC
Selecting most qualified contractor; typically, limited marketplace experience
Opportunities |  | Obstacles |  | Rating
FALSE | Allows for qualifications-based contractor procurement | FALSE | Currently there is not a large pool of contractors with experience in CM/GC, which will reduce the competition and availability
FALSE | Agency has control over an independent selection of best qualified designer and contractor
|  | FALSE | Working with only one contractor to develop GMP can limit price competition
FALSE | Contractor is part of the project team early on, creating a project “team”
|  | FALSE | Requires a strong project manager from the agency
FALSE | Increased opportunity for innovation due to the diversity of the project team
|  | FALSE | Teamwork and communication among the project team

## Summary Form
Project Delivery Selection Summary (Form M)
Complete the summary form below, based on your general evaluations for the primary and secondary evaluation factors from Forms E-L.
PROJECT DELIVERY METHOD OPPORTUNITY/OBSTACLE SUMMARY
| DBB | DB | CM/GC
Primary Evaluation Factors | 0 | 0 | 0
Delivery Schedule (Form E) | 0 | 0 | 0
Project Complexity/Innovation (Form F) | 0 | 0 | 0
Design Completion (Form G) | 0 | 0 | 0
Costs (Form H) | 0 | 0 | 0
Risks (Form I) | 0 | 0 | 0
Secondary Evaluation Factors | 0 | 0 | 0
Staff Experience and Availability (Form J) | 0 | 0 | 0
Oversight and Control Levels (Form K) | 0 | 0 | 0
Competition and Contractor Experience (Form L) | 0 | 0 | 0