## Form A
Project Description (Form A)
The following items should be considered when describing the project. Other items can be added to the bottom of the form if they influence the project delivery decision. Relevant documents can be included as appendices to the final summary report.
PROJECT ATTRIBUTES
PROJECT NAME:
PROJECT CORRIDOR OR LOCATION:
ESTIMATED BUDGET:
ESTIMATED PROJECT DELIVERY PERIOD:
REQUIRED DELIVERY DATE (IF APPLICABLE):
SOURCE(S) OF PROJECT FUNDING:
MAJOR FEATURES OF WORK – PAVEMENT, BRIDGE, SOUND BARRIERS, ETC.:
MAJOR SCHEDULE MILESTONES:
MAJOR PROJECT STAKEHOLDERS:
MAJOR OBSTACLES (AS APPLICABLE)
LIMITATIONS WITH RIGHT OF WAY, UTILITIES, AND/OR ENVIRONMENTAL APPROVALS: CRITICAL MILESTONES AND REQUIREMENTS DURING CONSTRUCTION PHASE: MAIN IDENTIFIED SOURCES OF RISK: SAFETY ISSUES: SUSTAINABLE DESIGN AND CONSTRUCTION REQUIREMENTS
CRITICAL MILESTONES AND REQUIREMENTS DURING CONSTRUCTION PHASE: MAIN IDENTIFIED SOURCES OF RISK: SAFETY ISSUES: SUSTAINABLE DESIGN AND CONSTRUCTION REQUIREMENTS
MAIN IDENTIFIED SOURCES OF RISK:
SAFETY ISSUES:
SUSTAINABLE DESIGN AND CONSTRUCTION REQUIREMENTS:

## Form B
Project Goals (Form B)
An understanding of project goals is essential to selecting an appropriate project delivery method; therefore, project goals should be set prior to using the project delivery selection matrix. Typically, the project goals can be identified in three to five items and should be reviewed here. Example goals are listed below, but the report should include project-specific goals, which should remain consistent over the life of the project.
PROJECT-SPECIFIC GOALS
GOAL #1:
GOAL #2:
GOAL #3:
GOAL #4:
GOAL #5:
Typical Project Goals
Schedule • Minimize project delivery time • Complete the project on schedule • Accelerate start of project revenue Cost • Minimize project cost • Maximize project budget • Complete the project on budget • Maximize the project scope and improvements within the project budget Quality • Meet or exceed project requirements • Select the team that brings the best value to the project • Provide a high-quality design and construction constraints • Provide an aesthetically pleasing project Functionality • Maximize the life cycle performance of the project • Maximize capacity and mobility improvements • Minimize inconvenience to the traveling public during construction • Maximize safety of workers and traveling public during construction

## Form C
Project Constraints (Form C)
There are potential aspects of a project that can eliminate the need to evaluate one or more of the possible delivery methods. A list of general constraints can be found below the table and should be referred to after completing this worksheet. The first section below is for general constraints and the second section is for constraints specifically tied to project delivery selection.
PROJECT-SPECIFIC CONSTRAINTS
CONSTRAINT #1:
CONSTRAINT #2:
CONSTRAINT #3:
CONSTRAINT #4:
CONSTRAINT #5:
Typical Project Constraints
Schedule • Utilize federal funding by a certain date • Complete the project on schedule • Weather and/or environmental impact Cost • Project must not exceed a specific amount • Minimal changes will be accepted • Some funding may be utilized for specific type of work (bridges, drainage, etc.) Quality • Must adhere to standards proposed by the Agency • Trying to balance quality design with construction limitations/constraints/abilities • Adhere to local and federal codes Functionality • Minimum number of lanes to be maintained during construction • Hazardous site where safety is a concern • Return area surrounding project to existing condition

## Form D
Project Risks (Form D)
Below is a general risk checklist of items to consider in the development, design, and construction of the project.
ENVIRONMENTAL RISKS |  | EXTERNAL RISKS
FALSE | Delay in review of environmental documentation | FALSE | Influential stakeholders request additional needs to serve their own commercial purposes
FALSE | Challenge in appropriate documentation | FALSE | Stakeholders request late changes
FALSE | Defined and non-defined hazardous waste | FALSE | Local communities pose objections
FALSE | Environmental regulation changes | FALSE | Community relations
FALSE | Environmental impact statement (EIS) required | FALSE | Intergovernmental agreements and jurisdiction
FALSE | Environmental analysis on new alignments required | FALSE | Conformance with regulations/guidelines/design criteria
FALSE | NEPA/ 404 Merger Process required
THIRD-PARTY RISKS |  | GEOTECHNICAL AND HAZMAT RISKS
FALSE | Unforeseen delays from utility owner/third-party | FALSE | Unexpected geotechnical issues
FALSE | Encounter unexpected utilities during construction | FALSE | Hazardous waste site analysis incomplete/in error
FALSE | Cost sharing with utilities not as planned | FALSE | Surveys late and/or in error
FALSE | Utility integration with project not as planned | FALSE | Inadequate geotechnical investigations
FALSE | Third-party delays during construction | FALSE | Adverse groundwater conditions
FALSE | Coordination with other projects/developers | FALSE | Other general geotechnical risks
FALSE | Coordination with other government agencies
RIGHT-OF-WAY/ REAL ESTATE RISKS |  | DESIGN RISKS
FALSE | Railroad involvement | FALSE | Design is incomplete/ Design exceptions
FALSE | Excessive relocation or demolition | FALSE | Scope definition is poor or incomplete
FALSE | Acquisition ROW problems | FALSE | Project purpose and need are poorly defined
FALSE | Difficult or additional condemnation | FALSE | Communication breakdown with project team
FALSE | Additional ROW purchase due to alignment change | FALSE | Pressure to deliver on an accelerated schedule
|  | FALSE | Constructability of design issues
FALSE | Objections to ROW appraisal take more time/money | FALSE | Project complexity - scope, schedule, objectives, cost, and deliverables - are not clearly understood
ORGANIZATIONAL RISKS |  | CONSTRUCTION RISKS
FALSE | Inexperienced staff assigned | FALSE | Pressure to deliver on an accelerated schedule
FALSE | Functional units not available or overloaded | FALSE | Inaccurate contract time estimates
FALSE | No control over staff priorities | FALSE | Construction QC/QA issues
FALSE | Lack of coordination/ communication | FALSE | Unclear contract documents
FALSE | Local agency issues | FALSE | Construction sequencing/staging/ phasing
FALSE | Internal red tape delay approvals, decisions | FALSE | Maintenance of Traffic/ Work Zone Traffic Control
FALSE | Losing critical staff at crucial point of the project
FALSE | Too many projects/ new priority projects inserted into program